## Gantt Chart
AI Cost Autopilot: Gantt Chart (Semester Plan)
Source: docs/roadmap.md, weeks 4 to 17. Edit the blue Start / End week cells and the bars move with them.
# | Task | Start week | End week | Duration (weeks) | Type | Milestone | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
1 | Project proposal | 4 | 4 |  | Work | Proposal report
2 | Gateway pass-through, freeze interfaces | 5 | 6 |  | Work
3 | v1 of trimmer, cache and autopilot | 5 | 6 |  | Work
4 | Prototype: end-to-end build | 7 | 7 |  | Work | Prototype demo (MST)
5 | Improvement plan from feedback | 8 | 8 |  | Work
6 | MST period | 9 | 10 |  | Break
7 | Semantic cache, second language, tuning | 11 | 12 |  | Work
8 | Integrate and measure savings | 11 | 12 |  | Work
9 | Buffer (holiday week) | 13 | 13 |  | Break
10 | Full integration, benchmark across tools | 14 | 15 |  | Work | Second prototype
11 | Improvements over second prototype | 16 | 16 |  | Work
12 | Final prototype, presentation, report | 17 | 17 |  | Work | Final deliverable (EST)
Legend
Project work
Exams / holiday (no planned work)
[7 empty] | ◆ | Milestone, due at the end of that week
[7 empty] | 123 | Blue text = input you can edit (start week, end week, type)
Note on C4: Week numbers of the semester, from docs/roadmap.md.